TN EMSC - 2010-2013 STRATEGIC PLAN
MISSION:  To ensure that every child in Tennessee receives the best pediatric emergency care in order to eliminate the effects of severe illness and injury.

VISION:      To be the foremost advocate for children throughout the continuum of care in Tennessee and the nation.

	GOAL #1: Develop specific communication tools to drive and promote TN EMSC’s mission to our members and communities

Committee members:  Sue Cadwell, and Paula Denslow Co-Chairs, Barry Gilmore ,  Eric Clauss, Susan Veal, and Chris Clarke()

	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	1.  Develop a marketing plan with a focus on public awareness of TN EMSC
	1. A marketing plan has been secured, implemented, increased awareness and has sustained funding for continue public relations.
	1.  Increased awareness of the public to the existence and function of TN EMSC
	1a.  The committee will Secure marketing group that will provide pro bono services for purposes of: 

-Determining Baseline Awareness of TN EMSC by  the Public
-Propose a marketing plan to include a budget estimate for deployment, 

  • Identifying a distribution and implementation pattern for the marketing proposal

    The committee will then:

-Propose the estimate to the finance committee who will then give us potential resources for funding

	1. Launch marketing plan

Establish indicators of success; website traffic, increased funds

Data collection of educational outreach CRPCs
	1.   Evaluate success of plan 
Refine plan based on awareness

Follow-up survey to measure public awareness

Identify ongoing partners for sustained funding


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	2.  Communicate  strategic plan in support of the TN EMSC mission to our members, member organizations and the public

	2.  Website organization alignment with strategic plan.  Member commitment is demonstrated by signing the “Eric Wall of Commitment” and member activities are in alignment with strategic plan.
	2.  Recognition of TN EMSC plan by members and member organizations
	      1b. Create an EMSC information slide or slides providing a description of EMSC, its history and accomplishments for members and other committees to add to their presentations. Eric Clauss to develop draft for January.
2a. Provision of the Strategic plan for each member by:

-Posting strategic plan on website by Kristi by May 11, 2010

-The CoPEC chair will review strategic plan and progress toward  annual goals at each meeting 
	2.  Yearly awareness survey for members and member organizations


	2.  Yearly awareness survey for members and member organizations




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	-Perhaps in conjunction with other committees, a yearly awareness survey for members and member organizations in order to gauge awareness of both the strategic plan itself as well as toward annual goals by October, 2010.  

2b.  The TN EMSC / CoPEC staff will Create, post, and have members sign “Eric Wall of Commitment” on May 11, 2010

2c.Kristi and Rhonda will seek permission to post “Meet Eric” (the TN Star of Life story about Eric) on youtube.com by April 30, 2010.  


	
	


	GOAL #2: To expand membership orientation and leadership capacity to address the various components of TN EMSC including CoPEC

Committee:  Rita Westbrook, and Debi Tuggle Co-Chairs, Carolyn Jackson, Diana Eckroth, Kate Copeland, Debi Tuggle, Jennifer Radtke


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	1.  Develop member orientation to increase knowledge capacity of CoPEC and TN EMSC


	100% participation in orientation of existing (em) and new members (nm)


	10

11

12

em

100

100

100

nm

100

100

100


	Orientation PowerPoint 

content:

1.  History updated by Debbie and Jennifer by August, 2010

2.  Funding structure PowerPoint: Carolyn and Diana completed by Carolyn and Diana by August 2010
3.  Organization /flow chart  completed by -May 2010-Rita

4.  Introduction to leadership/work groups slide-completed by Rita August 2010

5.  Expectation of members: to be pulled from bylaws –Jennifer by Aug 2010.

	Continue to offer quarterly orientation-by task force members
	Web based orientation Membership committee


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	6.  Update and arrange photo directory by regions completed by Kristi

7.  Brief review of strategic plan-Compiled from all of the various task forces and Rita by August 2010.

1b .Development of a  Big Brother/Sister program-guideline development by Dianne August 2010


	Implement plan of assigning big brothers/sisters- Dianne and chairs of Membership


	Evaluation of program via evaluations from both parties -Dianne




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	2.  Member development


	Completion of all training sessions by 80 % of the members


	10

11

12

LE

90%

RR

50

60

80

Civic

50

60

80

***

%

%

%

Call

10

20

Letter

10

20

Visit

10

20

*LE: leadership exercise

RR:  Roberts Rules of Order

baseline from survey


	Education Robert Rules of Order.

 4 sessions:

1.  Definitions/call to business-Jennifer August 2010

2.Classifications of motions-Kate October 2010

3.Committees and informal actions- Diane  Feb. 2011
4.Debates and voting/order of business and agenda- Carolyn –May 2011     
Sessions to be given over 1 year and repeated every 2 years. To be given at quarterly meetings by task force.

	Complete sessions for  1st cycle, evaluate with survey/evaluations

Development of education on the legislature process;

Rhonda and Carolyn Feb. 2011


	Development of new leaders and to offer a leadership workshop  

How do we determine the new leaders:

Input from current chairs:

Members who express interest

Responsible person: Membership committee

Continue education on RR  and  Civic course




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	3.  Professional update


	100%

compliance  of

work group chair responsibility completed


	10

11

12

TFR

85

90

90

EOR

85

90

90

TFR –task force written report to EMSC office

EOR-EMSC Office report to members


	Evaluate sessions by

Bi-annual survey

Civic/Law assessment:

Obtain base line on current members knowledge with survey –Carolyn Jackson with help form Kristi and survey Monkey. Have survey out by August 2010 

Work group chair to provide written report/minutes 2 weeks before CoPEC meeting –responsibility of each chair

EMSC  office to mail report to membership one week prior to meeting-Kristi and Rhonda
	Encouragement of increased civic participation through call, letters ad legislative visits


	Reassess members participation via survey

Arrange field trips for members to capital hill

Responsible party Rhonda and committee members




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	90 % of members attend 75% of quarterly meetings

100% of quarterly meetings have legislative update from Executive Director


	10

11

12

%

%

%

ATT

85

90

90

10

11

12

%

%

%

ED R

100

100

100

EDR-EX.DIRECTOR REPORT
	Send nomination letters for membership to each professional org or CEO represented on CoPEC – completed and return date is May 1, 2010

Present nominations to nominating committee and BLHCF and EMS board August 2010
	
	Send nomination letters for membership to each professional org or CEO represented on CoPEC – by TN EMSC office return date is May 1, 2012

Present nominations to nominating committee and BLHCF and EMS board May 2012


	GOAL #3: To develop and integrate a statewide disaster plan for children

Co-Chairs: James O’Donnell, Angie Bowen            Members: Marvin Hall, Anne Haston, Joe Holley, Mark Meredith, Gregg Mitchell, Joe Phillips, Ann Rutherford Reed, Patti Scott, Sheri Smith


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	1.  Integrate and interface TN EMSC disaster issues into Tennessee’s established disaster system

Lead: Angie Bowen 


	1a. Complete by July 1, 2010.

1b. Begin July 1, 2010 with completion by Dec.31, 2010. **Opportunities to share information with various agencies/organizations may present themselves and sharing information will be ongoing.


	2010: Obtain written state plan (ESF 8) and other pertinent existing information, and disseminate to committee. (Angie Bowen)  Done

	1a. Develop graph of agencies involved in disaster management in Tennessee and the relationships between each.  Obtain contact information for each agency.  (Angie Bowen)

** Patti Scott to obtain School Disaster Plan. Joe Phillips to obtain TEMA Plan with graph of interagency connection.


	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	1b.  Utilize above information to share information about TN EMSC and inquire as to needs of each agency in relation to pediatrics (All committee members based on specialty and geographic region, coordinated by Angie Bowen and James O’Donnell)

*Include RMCC/CRPC interface


	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	2.Write pediatric disaster addendum to Tennessee’s state disaster plan.

Lead: James O’Donnell

	2.Completion of written plan by December 31, 2011.

Initial step: Obtain previous work done by Dr. Abramo by December 31, 2009. (James O’Donnell) Done
Review of other state plans and work previously completed by December 31, 2010.  


	2010: Review of plans and work previously completed. Include altered standards of care.

2011: Completion of written plan.

2012: Submission of plan to state for acceptance into existing state disaster plan.


	2.Obtain copies of other state plans and begin review.

Sheri Smith

James O’Donnell

*Reference: Karen Ketchie

All committee members to review and submit feedback.


	2.  Completion of written plan.

James O’Donnell

Angie Bowen


	2.  Submission of plan to state for acceptance into existing state disaster plan.

James O’Donnell

Angie Bowen

Joe Phillips




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	3.Compile information and resources for dissemination/ready availability

Lead: Angie Bowen

	3.Material review by December 31, 2010. 

Resource compilation by December 
	2010: Material gathering and review 

2011: Resource compilation
	3.Materials gathered and reviewed. 

See assignments year 2.


	3. Compilation of resources to include:

-Pediatric treatment guidelines (Gregg Mitchell: Private Practice, Joe Holley: EMS/ED)

-Educational modules (Patti Scott, Marvin Hall, Anne Haston)

-Clearing house for classes with disaster/pediatric care components (PALS,PEPP, PITLS) (Angie Bowen)

-References (books, web/web-based links, DVD) (James O’Donnell)

-State and regional conferences (Mark Meredith)


	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	4.Develop tool for local pediatric disaster resources across the state.

Lead: James O’Donnell


	4a. Survey tool completed by December 31, 2010.  

4b.Hurtz information obtained by May 31, 2010.

4c. Map developed          

 county by 

 county by Dec. 31,    

 2011. 
	
	4a.  Develop survey tool for:

-EMS (Joe Holley, Angie Bowen)

-Hospitals (Mark Meredith, Sheri Smith, Anne Rutherford Reed)

-Private practitioners (Gregg Mitchell,  Patti Scott)
4b. Obtain information re: HURTZ system from state EMS office (James O’Donnell to obtain from Joe Phillips or Donna Tidwell by May 31, 2010.)


	Unless otherwise stated, all committee to research current availability. Angie Bowen to compile as a whole.

4.  Create resource map of the state county-by-county:

-ED care levels

-Hospital resources:          Inpatient services 

Bed availability/type

Surgical/subspecialty (especially ortho)

-Health Depts/clinics

-Pediatricians

-Family Practice

-Transport and referral patterns (RMCC)
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	5  .Organize statewide pediatric disaster drill

Lead: James O’Donnell

	5.  Completion of drill by December 31, 2012 


	**Mark Meredith to present to committee on SMART triage next meeting. Donna Tidwell or Joe Phillips to present on Hurtz system. 

5. 2012: Statewide disaster drill completed with data collected re: performance


	
	Angie Bowen and James O’Donnell to create from survey information obtained.

5.  Lay foundation for drill: 

-Type

- Scenario

- Literature/handouts/

   evaluation

- Agency approval

All committee members.


	5.Completion of statewide drill 

All committee members



	GOAL #4:  Use education (including publications) to support, develop and disseminate current best practice for emergency medical services for children

Marisa Moyers and Lee Blair, Co-Chairs    Kaye Stewart, Lee Blair, Yvette DeVaughn, Donna Tidwell , Michael Wallace, Trey Eubanks, Christy Cooper, Sandra Castro, Rick Collier, Ken Holbert,    Data co-chair Paulette Johnson, Brad Strohler


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	1.  Explore the implementation of a QI tool to be used statewide in identifying problematic EMS and inter-facility transports.


	1a.Increase participation and possible utilization of the QI process by CRPC facilities by 200% before July 2013.

1b.Decrease number of problematic transports by 50% before July 2013. 


	10

11

12

# of CRPC participation

1

1

2

10

11

12

ETCH

LeB

MCCH

TC T

Baseline by CRPC region

ETCH

Le Bonheur

MCCH@V

TC Thompson


	1a. Coordinators  and nurse managers to gather current QI data elements utilized at their CRPC institution and bring to coordinator meeting before August 12, 

2010 CoPEC meeting.

b. Establish general standards for problematic transfers (CRPC coordinators) Sept. 30

c.  Establish rating score for problematic transports (CRPC coordinators)  Sept 30

d.  Each CRPC region establish problematic 
	1a.Review problematic transfers from all 4 CRPCs and establish priority list of top five problems interventions by Feb 11, 2011

1b. Develop simulated intervention by May  2011

1c.  1st draft of publication regarding problematic transports to peer reviewed journal by Jan 2011 Final draft Feb. 2011

Target publication submission Feb. 2011.
	Investigate  the development of a strategy to expand QI tool at 4 general level pediatric facilities by June 2012

Complete simulated intervention development of #6-10 problematic transfers  by June 2012




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	d. Review redcap database to identify problematic transfers and cross-reference with transfers from identified hospitals by June 2010 (Paulette lead, Barb, Mark, Rhonda, and Sue C.)

e. Identify patients that received resuscitative measures at a non CRPC hospital and was not subsequently transferred from identified hospitals by June 2010

f. IRB generated between Vanderbilt and identified hospitals by June 2010 (Paulette and Sue C)2a.Task force members and CRPC coordinators, review materials from Susan Hohenhaus that were emailed from Rhonda
	1d 1st draft of publication to peer reviewed journal by Sept 2011 Final draft Oct. 2011

Target publication submission Feb. 2011.

Define early, on time, and late transfers (Paulette – lead plus task force members) by March 2011

Identification of early, on time and late transfers to Vanderbilt by May 2011  


	Lead for Strategy # 1 CRPC coordinators, ED nurse managers, and Paulette Johnson


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	2.  Develop Pediatric Simulation scenarios that will provide consistency in educational training.


	2. Each hospital facility that has an emergency department /

EMS services with an education agreement will be offered a pediatric simulation annually by 

CRPC coordinators


	10

11

12

ETCH

LeB

MCCH

TC T

Baseline by CRPC region

ETCH

Le Bonheur

MCCH@V

TC Thompson


	2a.Kaye, Lee, Donna and Stan plus the CRPC coordinators, review materials from Susan Hohenhaus that were emailed from Rhonda

b.CRPC coordinators identify scenarios problematic for all regions

c. Develop uniform curriculum used by each CRPC coordinator for scenario education that includes recognition of ill child, preparation for transfer, and appropriate handoff (CRPC coordinators and this task force) Feb 2011


	2.  Take information learned from above research and add to curriculum previously developed by Aug. 2011


	2. Publish initial pilot, written by CRPC coordinators and submitted to peer reviewed journal by Aug. 2012.
Lead for Strategy 2

Kay, Lee, Donna T., *Stan, CRPC Coordinators and Sandra Castro


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	d.  Develop standardize evaluation tool to critic scenario (CRPC coordinators and this task force) First draft Oct 2010 Final Feb. 2011

e. Develop evaluation tool for EMS and emergency department to complete following educational experience (CRPC coordinators and this task force)  First draft Oct 2010 Final Feb. 2011


	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	3.  Survey education tool for EMS

4.Basic pediatric emergency care presentations ABC


	3.The CoPEC education/data task force’s pre hospital education survey will be disseminated to 100% of ambulance services in TN with a 50% response to survey

4.  A basic pediatric emergency care presentation will be viewed by 75% of EMS agencies by 2012.


	Survey Response Rate

June 20%

July 30%

Aug 50%

Basic care presentation

10

11

12

Goal

25%

50%

75%

ETCH

LeB

MCCH

TC T


	3. Develop EMS education survey (Donna, Ken, Rick ) Encourage response to receive 50%

a.  Donna Tidwell to distribute survey through the EMS consultants

b.   CRPC coordinators to disseminate and tabulate survey in their respective regions and report results to task force by August 2010

c. Task force comprised of Donna, Rick, Lee and Ken
4.   Develop basic pediatric emergency care presentations (ABC) in the format requested in survey by October 2010

Develop pre and post test standardized presentations (all members of committee)


	4. Refine presentation using evaluation results by May 2011


	Lead for Strategy 3 Donna T., Rick Collier, and Ken Holbert
Lead for Strategy 4: Christy Cooper, *Kaye, and Sandra Castro, Rick Collier


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	5. Surveyor education

6.  EMS and BLHCF invited to observe mock code


	5. An orientation to the BLHCF surveyors regarding the pediatric emergency care rules and regulations will be attended by 75% of surveyors in 2011

6. 100% of  (EMS board) EMS Directors and Trainers  and BLHCF will be offered to observe a mock code and 75 % will observe mock code 

	% Attended

2011

75%

11

12

Goal Invite
100

100

ETCH

LeB

MCCH

TC T


	5.  An offer to assist with orientation will be made to the BLHCF by the chair of the Exceeding the Performance Measure task force and/or CoPEC chair at the Sept. 2010 meeting.

6.  Invitation will be made to EMS board members that are not retiring June 2010 by CRPC coordinator and Rick for the region in which the EMS board member resides and 50% will observe a mock code by Sept. 2010.
	5.  Orientation developed by Marisa and Yvette to surveyors will be presented at their annual meeting by the chair of the Exceeding the Performance Measure task force and/or CoPEC chair

6a.  Invitation will be made to EMS board members that are new since June 2010 by CRPC coordinator and Rick for the region in which the EMS board member resides and 50% will observe a mock code by December 2011

6b.  Invitation will be made to BLHCF that are not retiring June 2010 by CRPC coordinator for the region in which the board member resides and 50% will observe a mock code by Dec 2011.
	5.  Orientation will be offered annually.

Lead for Strategy 5:

Yvette and Marisa

Lead for Strategy 6 CRPC coordinators and Ric Collier


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	11

12

Goal

50%

75%

ETCH

LeB

MCCH

TC T

11

12

Goal

50%

75%

ETCH

LeB

MCCH

TC T


	
	
	


	GOAL #5:  Secure Diverse Funding Sources to Increase Revenues by 50% (150,000 to 240,000)
Committee:  Michael Carr and Bob Roth, Co-Chairs Leslie Phelps, Foundation board)


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	1.  Establish matrix and standardized funding streams.


	
	2010

2011

2012

Current Grants

75%

66%

62%

FF

4

5
5
LW

2

2
3
D

1.5

2
4

CG

0

2
4

GE

2.5

5
6

FR

4

4

5

Dues

2

1
1
SL

1

2
3

EC

8
11
7
100%

100%

100%

Baseline

Current grant funding = $150,000 81%

Fall Fundraiser = FF $ 15,000  9%

LW= Letter Writing - $0

Donations = D - $3000

CG=Corporate Giving - 0

GE=Grant expansion - $0

Dues $3,000

SL = Star of Life (-$2000)

EC= Ed Conference - $15,000  9%
	2010

Current Grants

150K

FF

8K

LW

4K

D

3K

CG

0

GE

5K

FR

8K

Dues

2K

SL

1K

EC

26.4K


	2011

Current Grants

150K

FF

12K

LW

5K

D

5K

CG

5K

GE

10K

FR

9.5K

Dues

2K

SL

2K

EC

30K


	2012

Current Grants

150K

FF

11.5K

LW

6K

D

10K

CG

10K

GE

15K

FR

11K

Dues

2K

SL

7K

EC

30K




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	1A) Educational conference has achieved increase in attendance and funds raised by 14% cumulative for optimal organizational stability. Rolling average of last 5 years plus 10%
1B)  The letter writing campaign “Friends of TN EMSC” has achieved participation from 100% of board members and 25% of TN EMSC colleagues in 10 followed by 10% cumulative annually.


	2010

2011

2012

#’s

180

205

235

$

26.4K

30K

30,K

Baseline 2009

Attendees    139

Amount raised    20,400
10

11

12

% 

Bd. 
100

100

100

%

Part
10

20

25

%

FG

2

2.2

2

Bd=Board Memb.

Part=Participants

FG=Funding Goal


	1A)   Identify a chairperson by July 1.

2A)   Committee to start work by Jul 1.

3A)   Event date and venue selected by 

 Sept 1 MC to talk w Barry and Ryan.
1B)   Enlist personal

letter writing campaign by Michael at Aug meeting (draft by MC and BR by Jul1)
· 100% of board members

· 10% of TN EMSC colleagues

2B)   Draft letters presented by 100% of board members and 10% of TN EMSC colleagues by Oct.

3B)   Letters mailed by November 1st.Incorporate “Giving” Thermometer into B and C by GS&F
	1A)   Identify a chairperson by July 1.

2A)   Committee to start work by Jul 1.

3A)   Event date and venue selected by 

 Sept 1
1B)   Enlist personal

letter writing campaign by Michael at Aug meeting (draft by MC and BR by Jul1)
· 100% of board members

· 10% of TN EMSC colleagues

2B)   Draft letters presented by 100% of board members and 10% of TN EMSC colleagues by Oct.

3B)   Letters mailed by November 1st.Incorporate “Giving” Thermometer into B and C by GS&F
	1A)   Identify a chairperson by July 1.

2A)   Committee to start work by Jul 1.

3A)   Event date and venue selected by 

 Sept 1
1B)   Enlist personal

letter writing campaign by Michael at Aug meeting (draft by MC and BR by Jul1)
· 100% of board members

· 10% of TN EMSC colleagues

2B)   Draft letters presented by 100% of board members and 10% of TN EMSC colleagues by Oct.

3B)   Letters mailed by November 1st.Incorporate “Giving” Thermometer into B and C by GS&F


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	1C)  Achieve individual giving by 100% of board members and 40% of TN EMSC colleagues


	10

11

12

%

BD

100

100

100

%

TN EMSC Friends 

20

30

40


	1C)   Enlist 100% of board members to make annual gift.

2C)   Enlist 20% of TN EMSC colleagues to make annual gift.

3C)   Implement record keeping process to record activity.

4C)   Establish goal of each board member giving $1000 as a result of Personal activity. 


	1C)  Enlist 100% of board members to make annual gift.

2C)  Enlist 30% of TN EMSC colleagues to make annual gift.

3C)  Implement record keeping process to record activity.

4C)  Establish goal of each board member giving $1000as a result of personal activity. 


	1C)  Enlist 100% of board members to make annual gift

2C)  Enlist 40% of program participants to make annual gift

3C)   Implement record keeping process to record activity

4C)   Establish goal of each board member giving $100 as a result of personal activity. 




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	1D) Achieve corporate giving.


	2010

2011

2012

CG

0

5000

10,000

100%

100%

100%

Baseline

CG=Corporate Giving - 0


	1D)   Compile list of possible funding for program dollars from corporations.

2D)    Investigate United Way/Community Giving to determine feasibility of participation in each region of the state by Rhonda Aug metg
3D)   Identify corporations that have a matching program by TN EMSC Friends.


	1D)  Compile list of possible funding for program dollars from corporations.

2D)  Participate in United Way/Community Giving to if feasibility indicates participation.

3D) Ten percent increase for number of donors of that have a matching program.

4D).  Nascar project to secure 3-5 years of financial commitment Carr, Staff


	1D) Compile list of possible funding for program dollars from corporations.

2D) Participate in United Way/Community Giving if warranted to continue.

3D) Ten percent increase for number of donors that have a matching program


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	1E)  Achieve expansion of grant funding.

1F) Expand number of fundraising activities.

1G)  Dues structure evaluation


	10

11

12

# of applications

2

4

4

# Awarded

2

2

2

Amt $

5k

10k

15k

100%

100%

100%

Baseline

GE-Grant expansion - 0


	1E)  Staff to identify possible grantors and timelines for submission.

2E)  Investigate ghost grant writer.

1F)  Add one additional anchor funding activity that raises $5,000.

1G)  Increase individual member dues to $40 per person


	1E)  Staff continues to identify possible grantors and timelines for submission.

2E)  Enlist persons to write grants.

1F)  2010 anchor increase funding activity that raises $9500.

1G)  Increase board membership dues to $150 per member


	1E)  Staff continues to identify possible grantors and timelines for submission.

2E) Enlist persons to write grants.

1F) 2010  anchor increase funding activity that raises $11,000

1G) Evaluate dues structure and  make recommendations to Board




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	1H) Star of Life

1I) Fall Fundraiser
	
	1H) Increase net proceeds by $ 1000

1I) Increase net proceeds by the rolling average of the past four years plus 10%

	1H) Increase net proceeds by $4000

1I) 1I) Increase net proceeds by the rolling average of the past four years plus 10%

	1H) Increase net proceeds by $7000

1I) 1I) Increase net proceeds by the rolling average of the past four years plus 10%



	GOAL #6:  Exceed the National EMSC Performance Measures

Statement of Direction:  EMSC performance measures are part of the foundation for providing quality pediatric emergency care.

Task Force Members:  Kevin Brinkmann, Barbara Shultz, Deena Kail, Randall Kirby, Joel Dishroon, Joe Holley


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 71:  The percent of pre-hospital provider agencies in the State/Territory that have on-line pediatric medical direction available from dispatch through patient transport to a definitive care facility.


	Increase from 85% to >90% the number ALS and BLS pre-hospital agencies that will have on-line pediatric medical direction from dispatch through patient transport to a definitive care facility by 2011. 


	09

10

11

71

85%

>90

72

85%

>90

73

11%/29%

>90

74

96%

>90

75

96%

>90

76

96%

>90

77

96%

>90

78

NO

YES

79

100

100

80

7/8

8/8

CAH

yes

CAH-congenital adrenal hyperplasia

	Obtain data of 2010 survey of ALS and BLS pre-hospital provider agencies.  Work with EMS CIC and EMS regional consultants to educate/ensure the provision of on-line pediatric medical direction for pre-hospital providers that do not have a plan for this in place.

Completed by R. Phillippi and CRPC coordinators by October 2010

Responsible Members:

Joel Dishroon

Randall Kirby


	Identify those ALS and BLS pre-hospital provider agencies that have not provided for on-line pediatric medical direction and continue to work with the EMS CIC and regional consultants to improve this.

Address possibility of adding on-line medical direction into the inspection reports.

Responsible Members:

Joel Dishroon

Randall Kirby


	Report to CoPEC and EMS CIC those ALS and BLS agencies that have not ensured on-line pediatric medical direction.  Further work with EMS CIC to ensure this support is available.

Project to be completed by July 2011.

Responsible Members:

Joel Dishroon

Randall Kirby
Link to Education  Goal


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 72:  The percent of pre-hospital provider agencies in the State/Territory that have off-line pediatric medical direction available from dispatch through patient transport to a definitive care facility.


	Increase from 85% to >90% the number ALS and BLS pre-hospital agencies that will have off-line pediatric medical direction from dispatch through patient transport to a definitive care facility by 2011.  


	
	Obtain data of 2010 survey of ALS and BLS pre-hospital provider agencies.  Work with EMS CIC and EMS regional consultants to educate/ensure the provision of off-line pediatric medical direction for pre-hospital providers that do not have a plan for this in place.

Completed by R. Phillippi and CRPC coordinators by October 2010

Responsible Members:

Joel Dishroon

Randall Kirby


	Identify those ALS and BLS pre-hospital provider agencies that have not provided for off-line pediatric medical direction and continue to work with the EMS CIC and regional consultants to improve this

Confirm that off-line protocols are addressed in the inspection reports.

Responsible Members:

Joel Dishroon

Randall Kirby


	Report to CoPEC and EMS CIC those ALS and BLS agencies that have not ensured on-line pediatric medical direction.  Further work with EMS CIC to ensure this support is available.

Project to be completed by 2011

Responsible Members:

Joel Dishroon

Randall Kirby




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 73:  The percent of patient care units in the State/Territory that have the essential pediatric equipment and supplies as outlined in national guidelines.


	Increase from 11% to >90% the number of BLS and 21% to >90% ALS ambulances that will have all the essential pediatric equipment and supplies necessary to provide quality pediatric emergency care by 2011.  


	
	1. Review the current National Guidelines and compare to current Tennessee equipment requirements for ALS and BLS ambulances.

2. Discuss/approve equipment changes in Task Force conference calls.

3. Present proposed equipment changes to CoPEC in 2010.

4. Dr. Brinkman to make recommendations to the EMS CIC in 2010. Ensure pediatric rep on EMS Task Force rewriting rules and regs. 

5. Dr. Holley to make recommendation for rulemaking changed at the Dec 2010 or March 2011 Board meeting to be in compliance with the National EMSC Performance Measure.


	Equipment changes presented to the EMS Board.

Equipment Rule changes communicated to the EMS agencies through the Regional EMS Consultants.

Responsible Members:

Dr. Brinkmann

Dr. Holley


	Ongoing review of updated National EMS equipment guidelines and future revision of Tennessee Rules as needed.




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	EMS Board Dates

2010

  March 24-25, 2010

June 23-24, 2010

September 22-23, 2010

December 1-2, 2010

2011

March 30-31, 2011

June 22-23, 2011

September 28-29, 2011

December 7-8, 2011

	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 74:  The percent of hospitals recognized through a statewide, territorial or regional standardized system that are able to stabilize and/or manage pediatric medical emergencies.


	All healthcare facilities that have the potential to stabilize and/or manage pediatric medical and/or traumatic emergencies are in compliance with their self-designated level of pediatric care as defined by the PECF Rules and Regulations.
	
	Data will be collected utilizing the national EMSC performance measure survey from greater than 80% of facilities capable of PM 74 and PM 75 by R. Phillippi and CRPC coordinators by Summer 2010.  

Need to assess if the remaining 4% are facilities that are capable of meeting these requirements (i.e. are those facilities primarily research hospitals such as St Jude Children’s Research hospital) and document that Tennessee has met these performance measures to the greatest ability.

Deena Kail responsible.  She will work with CRPC Coordinators to complete this PM by 2011. 


	Continue follow-up with facilities and document compliance with the National EMSC guidelines.


	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 75:  The percent of hospitals recognized through a statewide, territorial or regional standardized system that are able to stabilize and/or manage pediatric traumatic emergencies.


	For PM 74 and 75, on the last survey 96% of Tennessee’s health care facilities satisfy this requirement.  The national goal is for 25% by 2017 for PM 74 and 50% for PM 75.  
	
	
	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 76:  The percentage of hospitals in the State/Territory that have written inter-facility transfer guidelines that cover pediatric patients and that include the following components of transfer: (see reference)

PM 77:  The percentage of hospitals in the State/Territory that have written inter-facility transfer agreements that cover pediatric patients.
	Tennessee health care facilities will have transfer agreements that cover pediatric patients and will have transfer guidelines that include all the components of transfer as recommended by National EMSC.

Currently 96% of Tennessee health care facilities meet both of these performance measures.


	
	Data will be collected utilizing the national EMSC performance measure survey from greater than 80% of facilities capable of PM 76 and PM 77 by R. Phillippi and CRPC coordinators by Summer 2010.


	PECF Rules and Interpretive Guideline Review and Revision:

Kevin and Barbara to review the PECF Interpretive Guidelines documentation of the necessary components of the transfer guidelines.  Propose amendments to the interpretive guidelines as needed to be clear of these requirements by the end of 2010.  Review with CoPEC any additional changes to the PECF Rules and/or Interpretive Guidelines and finalize any proposed changes for presentation to the BLHCF by 2011.
	Universal Pediatric Transfer Agreement:

Kevin and Barbara to communicate with the CRPC and THA legal representatives regarding development of a universal pediatric transfer agreement in 2010.  Communicate with this legal group the components of transfer as per PM 76 to be included in this new universal transfer agreement in 2010.  Communicate with the legal group the potential for improving statewide disaster planning with a universal agreement.  Continue to follow and support the legal teams as able with proposed completion of project in 2011.




	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	
	
	
	Identify the health care facilities that currently do not have all the necessary components of the transfer agreement.  Communicate with those facilities the needed components for their written transfer guidelines.  Barbara and Deena to contact CRPC Coordinators for facilities with agreements that don’t have all guidelines.  CRPC Coordinators to educate those facilities in 2010 and 2011.  Further identify if the 4% of Tennessee health care facilities that did not meet these PM in the last survey are capable of meeting these PM.  Provide support to these facilities if they are able to meet these PM, otherwise document that Tennessee has met these PM to the greatest ability.


	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 78:  The adoption of requirements by the State/Territory for pediatric emergency education for the license/certification renewal of basic life support (BLS) and advanced life support (ALS) providers.


	Approval by the EMS Board for this requirement.


	
	Collaborate with TEMSEA, EMS CIC and EMS Education committee/Scope of Practice Committee on adoption of requirements for pediatric emergency education for license renewal of BLS and ALS providers.  At 8/9/07 COPEC meeting, motion was passed that 20% of EMS CEUs for recertification be in pediatrics -- communicate this to above stakeholders.

This is benchmarked to be completed in 2010 with a deadline for completion in 2011.  Plan to follow-up with the EMS Board and provide support as needed to ensure this change in rules.  Consider having the CRPC coordinators invite EMS Board Members to attend a mock code at one of their local EMS agencies.

Joel, Trisha, and Randall to lead these discussions.  


	Follow through with the changes in rules with the EMS Board to ensure adoption of requirements for pediatric emergency education for license renewal of BLS and ALS providers.

Joel and Randall to communicate with EMS regional consultants to communicate changes to EMS providers.


	Rules in place that provide for 100% compliance for this performance measure.

Link with Education committee


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 79:  The degree to which Tennessee has established permanence of EMSC in the State EMS System


	PM 79:  Permanence of EMSC in the State system is defined as:

a. EMSC Advisory Committee has the required members as per the implementation manual.

b. EMSC Advisory Committee meets at least 4 times a year.

c. By 2011,  pediatric representation will have been incorporated on the State EMS Board

d.By 2011, TN will mandate requiring pediatric representation on the EMS Board.

e.By 2011, one Full time EMSC Manager that is dedicated solely to the EMSC Program will have been established


	
	Continue to maintain compliance with all 5 objectives.


	
	


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	PM 80:  The degree to which the State/Territory has established permanence of EMSC in the State/Territorial EMS system by integrating EMSC priorities into statutes/regulations.


	TN EMS will have understanding of the National EMSC Performance measures and the need for establishing permanence of EMSC in Tennessee’s EMS system by integrating EMSC priorities into statutes/regulations.

1.Key stakeholders are able to demonstrate knowledge of EMSC performance measures and access them as needed.

A plan of action will have been completed by May 2011
	
	EMSC Performance Assessment

1.  Annual report card of TN achievement of EMSC performance measures to key stakeholders. Color coded, easy to read report card distributed to each region ends a statewide goal.

(Barb and Deena)

	
	Present score card to National EMSC office for further implementation/distribution.

Link to Communication tools task force


	STRATEGIES
	LEADING INDICATORS OF SUCCESS
	3 YEAR PERFORMANCE TARGETS
	YEAR 1 (10-11) ACTION PLANS & LEAD
	YEAR 2 (11-12) ACTION PLANS & LEAD
	YEAR 3 (12-13) ACTION PLANS & LEAD

	2.  Committee will have reviewed and developed action plan for children with congenital adrenal hyperplasia

	
	
	This PM 80 will be complete with the completion of PM 78.  Committee will then work on an annual report card.  This report card will be sent to COPEC Marketing (Goal #4 Communication) to be sent to stakeholders.

2. Emphasize performance measures that TN does not currently meet.

Information will be gathered from CARES as well as other states regarding plans for children with CAH- task force members

Action plan will be presented to CoPEC at August 2010 meeting

If approved, action plan proposed to Clinical Issues Committee of EMS Board by Dr. Brinkman at September 2010 meeting.
	
	Link with Education task force


PAGE  
1
[image: image1.png]3%

TN EMSC

Tennessee Emergency
Medical Services for Children






[image: image1.png]